## INSTRUCTIONS
INSTRUCTIONS
Please read these instructions carefully
This is your Project workbook
Click on the tabs along the bottom of the page to open the corresponding worksheets
Budget Table
Activity Table
Example Activity Table - for reference only
Evidence Table
For your Application, you will need to complete the relevant sections of the Budget Table and the Activity Table and submit the workbook to us via the online Application Form.
It is important that you keep a copy of the workbook after you have filled out the relevant sections as you will need it at the reporting stage if your Project receives our funding.
If we fund your Project, at the reporting stage you will update and complete the Budget Table (as part of your Final Grant Claim), the Activity Table and the Evidence Table.
and submit them along with receipted invoices and any evidence of project outputs to rebecca.foster@cotswolds-nl.org.uk
We will use these to assess whether your Project has been completed satisfactorily, which will allow the final Grant instalment to be released.

## BudgetTable
SECTION 1
Item | Predicted Cost (£) | Actual Cost (£) | Notes
SECTION 2
Funding sources | Amount Requested | Amount Received | Decision Date
Caring for the Cotwolds Grant Scheme
FOR OFFICIAL USE ONLY
Total project costs | 0 | 0
Total requested & received | 0 | 0
Funding shortfall | 0 | 0
EXPLANATORY NOTES
SECTION 1
Please list the item/service that you will be purchasing for your project (e.g. building materials; grass cutting; tent hire)
Please insert additional rows as required
Predicted Cost - please state the expected cost of the item in £; only include VAT if you are unable to reclaim it
Actual Cost - if your Application is successful, you will fill in this column at the end of your Project as part of your financial reporting and submit with receipted invoices; only
include VAT if you are unable to reclaim it
Notes - please use this space if you want to provide further details about the items or their cost
SECTION 2
Please list all the sources of funding for your Project, the amount requested or received, and the date that the decision was or will be made
Note that the first row is where you indicate how much you are requesting from us

## ActivityTable
SECTION 1: APPLICATION |  |  |  | SECTION 2: FINAL REPORT - ONLY complete this section as part of your Final Report if we fund your Project
Planned date | Activity | Expected Output | Expected Outcome | Delivered Output | Date delivered | Are you submitting evidence of the Delivered Output? |  | Does the Delivered Output differ from the Expected Output? |  | Did you achieve the Expected Outcome?
[6 empty] | (Yes/No) | If YES, please state what | (Yes/No) | If YES, please explain why | (Yes/No) | Please explain where appropriate
EXPLANATORY NOTES
SECTION 1 - complete this section as part of your Application to us
To be completed at the Application stage
For each Activity in your Project, please indicate the date that you plan to do this Activity, and describe what the Activity is, the Expected Output(s) of the Activity, and the subsequent Expected Outcome(s);
you may have more than one Expected Output for a single Activity, if so, please use a new row for each Expected Output
Outputs are the direct, tangible results of your activities e.g. length of path restored, number of trees planted, hectares of wildlife flowers planted, number children attending an educational activity
Outcomes are the improvements and impact of your activities e.g. improved public access to enjoy the Cotswolds, improved environmental and human well-being, increased wildflower species diversity,
improved understanding and appreciation of wildlife among school children
Please insert extra rows as required
SECTION 2 - only complete this section as part of your Final Report if we fund your Project
If we fund your Project, when you have completed your Activities you will need to fill out this section for submission as your Final Report
For each Activity in your Project, please describe the Ouput(s) that you delivered, the date that it was delivered, and whether and/or why it differed from the Expected Output(s)
For each Activity in your Project, please indicate what electronic evidence you are submitting to demonstrate that the Output(s) was delivered (e.g. photos, pdfs of reports, weblinks)
For each Activity in your Project which has an associated Expected Outcome, please explain whether the Expected Outcome was or is being achieved and describe any evidence to support this
If you added Activities during your Project that are not included in SECTION 1, please insert extra rows and fill in accordingly

## ActivityTable_example
SECTION 1: APPLICATION |  |  |  | SECTION 2: FINAL REPORT - ONLY complete this section as part of your Final Report if we fund your Project
Planned date | Activity | Expected Output | Expected Outcome | Delivered Output | Date delivered | Are you submitting evidence of the Delivered Output? |  | Does the Delivered Output differ from the Expected Output? |  | Did you achieve the Expected Outcome?
[6 empty] | (Yes/No) | If YES, please state what | (Yes/No) | If YES, please explain why | (Yes/No) | Please explain where appropriate
Feb 2026 | Purchase seeds, compost and gardening tools | Supplies and equipment available for hands-on horticultural sessions at our community farm | NA | Seeds, compost and gardening tools acquired | 2026-02-02 | Yes | Photo of supplies | No | NA | NA | NA
Feb 2026 | Give a presentation and question and answer session about the scheme at two local residential facilities for people with learning disabilities | 20 people who have additional needs, and their support workers, sign up to join sessions at the farm site | People who might not otherwise access the landscape have the opportunity to connect with nature | 18 people with additional needs, and their support workers, signed up; 10 from residential facility #1 and eight from residential facility #2 | 2026-02-05 | Yes | Photos of question and answer session | Yes | 18 people signed up, not 20 | Yes | Participants reported that they were excited to spend time outside and have the chance to work on a real farm
Feb-Oct 2026 | 38 half-day (4h) sessions run weekly over eight-month period which will involve: | - | - | - | - | - | - | - | - | - | -
Feb-Oct 2026 | (1) Informal teaching about native plants, growing food without chemicals, and how to support biodiversity | 20 people with additional needs, and their support workers, attend up to eight informal learning sessions, totalling 4 x 8 x 20 = 640 participant hours | Participants have improved knowledge about local plants, growing food organically, environmental protection, and biodiversity | 18 participants, and their support workers, attended eight informal learning sessions, totalling 4 x 8 x 18 = 576 participant hours | Feb-Oct 2026 | Yes | Photos of participants during informal learning sessions | Yes | 18 people signed up, not 20 | Yes | All participants gained in confidence talking about the work that they were doing on the farm and why organic methods help with protecing the environment and biodiversity
Feb-Oct 2026 | (2.1) Outdoor group activities planting, sustaining and harvesting fruit and vegetables, and maintaining and enhancing farm infrastructure | 20 people with additional needs, and their support workers, attend up to 30 outdoor activity sessions, totalling 4 x 30 x 20 = 2400 participant hours | Participants have improved physical and mental well being Participants develop new horticulatural skills and interests | 18 participants, and their support workers, attended 30 outdoor activity sessions, totalling 4 x 30 x 18 = 2160 participant hours | Feb-Oct 2026 | Yes | Photos of participants gardening | Yes | 18 people signed up, not 20 | Yes | Participants worked outside in all weather contibuting to their physical well being and developing perserverance; when asked about how they felt about the sessions some reported "It makes me happy when I come here" and "It was magical when we moved the hay" and "I liked harvesting the pumpkins". Participants developed different interests and skills e.g. caring for a particular crop, using a hammer and nails to build a poly tunnel, and shifting woodchip using a wheel barrow
Feb-Oct 2026 | (2.2) Outdoor group activities planting, sustaining and harvesting fruit and vegetables, and maintaining and enhancing farm infrastructure | Seasonal fruits and vegetatbles growing through spring and summer | Participants have an improved understanding of the full cycle from plant to plate | Participants grew and harvested: marrows, carrots, kale, tomatoes, corn, potatoes, pumpkins, strawberries and raspberries | Feb-Oct 2026 | Yes | Photos of participants growing fruit and vegetables | No | NA | Yes | Participants enjoyed returning each week to see how much their crops had grown, and sometimes requested to come sooner!
Feb-Oct 2026 | (2.3) Outdoor group activities planting, sustaining and harvesting fruit and vegetables, and maintaining and enhancing farm infrastructure | 20 people with additional needs, take home fruits and vegetables that they have grown organically | Participants cook with more seasonal produce or grow their own in the future | 18 participants took home fruits and vegetables that they grew organically | Jun-Oct 2026 | Yes | Photos of participants harvesting fruit and vegetables | Yes | 18 people signed up, not 20 | Yes | All participants reported that they enjoyed sharing, cooking and eating the produce; and 15 of the participants asked whether they could continue coming to planting and growing sessions next year
Feb-Oct 2026 | (3) Supported conversations throughout the sessions | 20 people with additional needs engage in supported conversations with one another, support workers and the project team | Participants build social connections | 18 participants engaged in conversations and developed friendships with one another, support workers and the project team | Feb-Oct 2026 | Yes | Photos of participants enjoying shared tea breaks | Yes | 18 people signed up, not 20 |  | There was a strong social element throughout the sessions, with a shared tea break in the middle; one participant started bringing a homemade nature-based quiz to the tea breaks and this soon became expected and everyone got involved
Feb-Oct 2026 | Social media posts about the supported-learning horticultural sessions at the community farm | Project description, activities and photos shared on our Facebook and Twitter accounts | Increased awareness about the project among the general public | Project description, activities and photos shared on Facebook, Twitter and LinkedIn | Feb-Oct 2026 | Yes | Link to posts | Yes | We set up a LinkedIn account to reach a larger audience | Yes | Our social media posts about the project have received 1000 likes and been shared 450 times
Oct. 2026 | Press release about project | Press release sent to local paper and local radio station | Interview requests from local paper and radio | Press release sent to three local papers and two local radio stations | 2026-11-01 | Yes | Press release (pdf) | Yes | We identified additional contacts for press releases | Yes | We received requests for interview from two local papers and one local radio station
Oct. 2026 | Interview on local radio and/or with local paper discussing the project and its benefits to the local community | At least one interview with the press/media | Increased awareness about the project among the general public leading to support for future similar projects | Interview with two local papers and one local radio station | 2026-11-10 | Yes | Link to online articles | Yes | We sent press releases to additional papers and radio stations so received additional invitations for interview | Yes | Following the interview on the radio we received calls from three organisations who would like to support us on future projects, and seven private individuals who wanted to get involved with our work

## EvidenceTable
Type of evidence | File name | File type or URL | Description | Credits
Photograph | Gardening_supplies | JPEG | Photo of seeds, compst and gardening tools purchased for the project | JSmith | EXPLANATORY NOTES - only complete this form as part of your Final Report if we fund your project
Photograph | Q&A_session | JPEG | Photo of Q&A session about the scheme at residential facility | JSmith | If we fund your project, please use this form at the Final Reporting stage
Photograph | Learning_plants | JPEG | Photo of participants learning about native plants | JSmith | Please use it to document any electronic evidence that you submit to us as proof of having delivered your Project Outputs
Photograph | Learning_biodiversity | JPEG | Photo of participants learning about biodiversity | TBrown | Please indicate the type of evidence (e.g. photograph, report, news article, map), the name of the file that you are submitting,
Photograph | Planting_seeds | JPEG | Photo of participants planting seeds | JSmith | the type of file (or the URL if it is a webpage), a description of what it shows, and if required, the name of anyone we need to credit
Photograph | Building_polytunnel | JPEG | Photo of participants building poly tunnel | TBrown | We have included some examples at the top of the form
Photograph | Tea_break | JPEG | Photo of participants enjoying the tea break | JSmith | Please insert additional rows as required
Photograph | Harvesting_pumpkins | JPEG | Photo of participants harvesting pumpkings | HWallace | Please send the files along with this Project workbook to rebecca.foster@cotswold-nl.org.uk as part of your Final Report
Facebook post | N/A | [provide link to post] | Post about project | N/A | Please note that we reserve the right to use for publicity and reporting purposes any images that you share with us.
Twitter post | N/A | [provide link to post] | Post about project | N/A | It is your responsibility to obtain the consent of any person photographed before sharing the image with us.
LinkenIn post | N/A | [provide link to post] | Post about project | N/A
Press release | PressRelease_CommunityFarmProject | pdf | Press release sent to the local press and media about our project | N/A
Online radio interview | N/A | [provide link to post] | Radio interview about our project | N/A
Online news article | N/A | [provide link to post] | News article about our project | N/A
Online news article | N/A | [provide link to post] | News article about our project | N/A